## Action Tracker
Task ID | Task | Owner | Due Date | Priority | Stakeholder | Status | Missing Information / Next Step | Last Updated
ACT-001 | Schedule and deliver Class 8 maths teacher demo at Maple Heights School (Gurugram) | Unassigned (Suggested: Founder 1 or Academic Lead) | Before 08-Nov-2026 | High | School | Not started | Demo date and presenter unconfirmed. Need dates before Diwali break (~8 Nov). | 23-Oct-2026
ACT-002 | Prepare first-month usage report for Maple Heights School (requested by Ms. Kapoor) | Unassigned | TBD | High | School | Not started | Due date not set. Metrics to include not defined. Need to check if Ms. Kapoor wants specific data. | 23-Oct-2026
ACT-003 | Request print quotation from PrintWorks for 300 teacher guides (budget cap Rs 40,000) | Unassigned (Suggested: Founder's Office Intern) | TBD | High | Vendor | Not started | Nobody has followed up yet. Need print specifications, page count, and quotation approver. | 23-Oct-2026
ACT-004 | Clarify invoice amount, verify deliverables, and process payment for content vendor | Unassigned | 30-Oct-2026 | High | Vendor | Blocked | Invoice amount not discussed in meeting. Invoice copy missing. Payment authorizer unconfirmed. | 23-Oct-2026
ACT-005 | Conduct quick review of 3 AI tutoring tools for K-12 India (requested by Founder 1) | Unassigned (Requested by Founder 1) | 30-Oct-2026 | Medium | Internal | Not started | Founder 1 requested this by next Friday (30 Oct 2026). Assignee not confirmed in notes. | 23-Oct-2026
ACT-006 | Review parent consent forms for DPDP compliance before expanding pilot to more classes | Unassigned | TBD (Precedes expansion) | High | Compliance | Blocked | No date set. Reviewer unassigned. Strictly blocks expanding the school pilot. | 23-Oct-2026
ACT-007 | Enter paper leads from school fair (collected two weeks ago) into central CRM | Unassigned | TBD | Medium | Internal | Not started | Leads sitting on paper for ~14 days. Owner and data-entry deadline not confirmed. | 23-Oct-2026
ACT-008 | Draft and send investor update | Founder 2 | 05-Nov-2026 | Medium | Investor | Not started | Founder 2 confirmed as owner. Internal draft review date not specified. | 23-Oct-2026
ACT-009 | Maintain single central tracker across all workstreams so no action slips | Founder's Office Intern | Ongoing | High | Internal | In progress | Confirmed owner is Founder's Office Intern. Central tracker active and maintained weekly. | 23-Oct-2026

## Decisions Log
Decision ID | Decision Required | Decision Owner | Context | Deadline | Decision Made | Date Confirmed
DEC-001 | Content vendor invoice amount, invoice copy, and payment authorizer | Founders | Invoice due 30 Oct. Amount not discussed in sync. | 26-Oct-2026 | Pending | TBD
DEC-002 | Presenter and format for Maple Heights teacher demo | Founders | Principal wants demo for Class 8 maths teachers before ~8 Nov. | 28-Oct-2026 | Pending | TBD
DEC-003 | Approver for PrintWorks quotation against Rs 40,000 cap | Founders | Budget cap Rs 40,000 for 300 copies. Quotation needed. | 27-Oct-2026 | Pending | TBD
DEC-004 | Reviewer for DPDP parent consent compliance | Founders | Required before pilot expansion to new classes. | 28-Oct-2026 | Pending | TBD
DEC-005 | Assignee for AI tutoring tools review | Founder 1 | Requested by Founder 1 by next Friday (30 Oct). | 26-Oct-2026 | Pending | TBD

## Follow-ups
Follow-up ID | Recipient | Stakeholder | Purpose | Reviewer | Approval Status | Sent Date
FOL-001 | Ms. Kapoor [Verified school contact] | School | Coordinate Class 8 maths demo dates and usage report requirements | Founders | Pending review | TBD
FOL-002 | PrintWorks Sales Desk [Verified vendor contact] | Vendor | Request print quotation for 300 teacher guides under Rs 40,000 budget cap | Founders | Pending review | TBD
FOL-003 | Founders (Internal Chat) | Internal | Seek immediate decisions on invoice, demo lead, print approver, and DPDP review | Founder's Office Intern | Ready to send | TBD